## Sobre
SOBRE ESTE GRÁFICO DE GANTT
Visualize e controle seus projetos usando este modelo de gráfico de Gantt. Para começar, insira as tarefas em que você está trabalhando na seção Descrição do Marco e insira os detalhes de cada tarefa. Os dados serão atualizados automaticamente e será fácil inserir novas tarefas ou usar a barra de rolagem para rolar pela linha do tempo.
• Use o Progresso para adicionar quanto do projeto você concluiu adicionando um número de porcentagem. • Adicione o dia de início do seu projeto na Data de Início. • Conclua os cálculos preenchendo o número de dias necessários para concluir o projeto No campo No. de Dias.

## Escuro
POWER MONITOR
Nome da empresa |  | HIGHLANDER'S |  |  |  | Legenda: | No prazo |  |  |  |  | Baixo risco |  |  |  |  | Médio risco | [5 empty] | Alto risco |  |  |  |  | Concluido
Líder do Projeto |  | TASSIO MANGUEIRA
Data de Início do Projeto: |  | 2026-06-03 |  |  |  |  | junho | [34 empty] | julho
Incremento de Rolagem: |  | -1 | time axis 2026-06-02 to 2026-07-27
TAG | Descrição do marco | Categoria | Tipo | A quem? | Início | Dias | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s
SD | System Design |  |  |  | 2026-06-03
SD-001 | Define MQTT Topic Structure | Concluído |  |  | 2026-06-03 | 1 | q: 0
SD-002 | Define MQTT Telemetry Payload Contract | Concluído | Predecessora | SD-001 | 2026-06-04 | 1 | q: 0
SD-003 | Define MQTT Heartbeat Contract | Concluído | Paralela | SD-002 | 2026-06-04 | 1 | q: 0
SD-004 | Design Ingestion Worker Service Contract | Concluído | Paralela | SD-003 | 2026-06-04 | 1 | q: 0
SD-005 | Design Telemetry Aggregation Strategy | Concluído | Predecessora | SD-004 | 2026-06-05 | 2 | s: 0; s: 0
SD-006 | Design REST API Contract | Médio risco | Paralela | SD-005 | 2026-06-05 | 2
SD-007 | Create Sequence Diagrams | Médio risco | Paralela | SD-006 | 2026-06-05 | 2
SF | Solution Foundation |  | Predecessora | SD-007 | 2026-06-09
SF-001 | Create Solution Structure | No prazo | Paralela | SF | 2026-06-09 | 3
SF-002 | Configure Shared Infrastructure Project | No prazo | Paralela | SF-001 | 2026-06-09 | 3
SF-003 | Implement Domain Entities | No prazo | Predecessora | SF-002 | 2026-06-12 | 3
SF-004 | Implement EF Core Configurations | No prazo | Paralela | SF-003 | 2026-06-12 | 3
DB | Database Layer |  | Predecessora | SF-004 | 2026-06-17
DB-001 | Create Initial Migration | No prazo | Paralela | DB | 2026-06-17 | 1
DB-002 | Generate Database Schema | No prazo | Paralela | DB-001 | 2026-06-17 | 1
DB-003 | Seed Default Data | No prazo | Paralela | DB-001 | 2026-06-17 | 1
DB-004 | Validate Query Performance | Objetivo | Paralela | DB-001 | 2026-06-17 | 4 | q: 2; q: 2; s: 2; s: 2
TI | Telemetry Ingestion Service |  | Predecessora | DB-004 | 2026-06-23
TI-001 | Configure MQTT Client | No prazo | Paralela | TI | 2026-06-23 | 2
TI-002 | Implement MQTT Topic Subscriptions | No prazo | Paralela | TI-001 | 2026-06-23 | 2
TI-003 | Implement Payload Validation | No prazo | Predecessora | TI-002 | 2026-06-25 | 2
TI-004 | Persist TelemetrySample Records | Objetivo | Paralela | TI-003 | 2026-06-25 | 3 | q: 2; s: 2; s: 2
TI-005 | Update Monitor Heartbeats | No prazo | Predecessora | TI-004 | 2026-06-30 | 1
AG | Aggregation Engine | Marco | Predecessora | TI-005 | 2026-07-01
AG-001 | Implement Minute Aggregation | No prazo | Paralela | AG | 2026-07-01 | 2
AG-002 | Implement Hourly Aggregation | No prazo | Paralela | AG-001 | 2026-07-01 | 2
AG-003 | Implement Daily Aggregation | No prazo | Paralela | AG-002 | 2026-07-01 | 2
AG-004 | Implement AggregationCheckpoint Logic | No prazo | Predecessora | AG-003 | 2026-07-03 | 2
API | Energy Analytics API |  | Predecessora | AG-004 | 2026-07-07
API-001 | Room CRUD | No prazo | Paralela | API | 2026-07-07 | 2
API-002 | Monitor CRUD | No prazo | Paralela | API-001 | 2026-07-07 | 2
API-003 | Channel Queries | No prazo | Predecessora | API-002 | 2026-07-09 | 2
API-004 | Channel Assignment Management | No prazo | Paralela | API-003 | 2026-07-09 | 2
API-005 | Energy Tariff Management | No prazo | Predecessora | API-004 | 2026-07-13 | 2
API-006 | Telemetry Query Endpoints | No prazo | Predecessora | API-005 | 2026-07-15 | 2
E2E | End-to-End Validation |  | Predecessora | API-006 | 2026-07-17
E2E-001 | ESP32 → MQTT → SQL Server | Objetivo | Paralela | E2E | 2026-07-17 | 2 | s: 2; s: 2
E2E-002 | Telemetry Aggregation Validation | Objetivo | Paralela | E2E-001 | 2026-07-17 | 2 | s: 2; s: 2
E2E-003 | Assignment History Validation | Objetivo | Paralela | E2E-001 | 2026-07-17 | 2 | s: 2; s: 2
E2E-004 | Cost Calculation Validation | Objetivo | Paralela | E2E-001 | 2026-07-17 | 2 | s: 2; s: 2
Para adicionar mais dados, insira novas linhas ACIMA desta.
Note on C11: Author: Goal: - Fully specify the system before implementation.
Note on C12: Author: Acceptance Criteria: - Topic hierarchy documented - Telemetry topics defined - Heartbeat topics defined - Naming conventions documented Deliverable: - mqtt-contract.md
Note on C13: Author: Acceptance Criteria: - JSON schema documented - Versioning strategy defined - Validation rules defined - Example payloads included Deliverable: - mqtt-contract.md
Note on C14: Author: Acceptance Criteria: - Heartbeat payload defined - Online/offline strategy documented Deliverable: - mqtt-contract.md
Note on C16: Author: Acceptance Criteria: - Minute aggregation defined - Hourly aggregation defined - Daily aggregation defined - Checkpoint strategy defined Deliverable: - aggregation-design.md
Note on C17: Author: Acceptance Criteria: - All public endpoints documented. - Request and response schemas defined. - Standard error model defined. - Resource ownership boundaries defined. - Resource identity strategy defined. - URL and route conventions defined. - HTTP method semantics defined. - HTTP status-code mapping defined. - Pagination strategy defined. - Filtering and sorting conventions defined. - UTC timestamp and time-range semantics defined. - Historical query semantics defined. - Projection completeness exposure defined. - Idempotency expectations defined where applicable. - Concurrency strategy defined for mutable resources. - API versioning strategy defined. - Authentication and authorization boundary identified, even if implementation is deferred. - Internal operational state explicitly excluded or separately scoped. - OpenAPI deliverable structure defined. Deliverable: - api-specification.md
Note on C18: Author: Acceptance Criteria: - Telemetry ingestion flow - Assignment flow - Aggregation flow Deliverable: - sequence-diagrams.md
Note on C19: Author: Goal: - Create the .NET solution skeleton.
Note on C20: Author: Deliverables: - EnergyAnalytics.sln - Energy.Domain - Energy.Infrastructure - Energy.API - Energy.TelemetryIngestion
Note on C21: Author: Acceptance Criteria: - SQL Server configured - EF Core configured - Migrations enabled
Note on C22: Author: Entities: - Room - Monitor - Channel - ChannelAssignment - TelemetrySample - TelemetryMinute - TelemetryHourly - TelemetryDaily - EnergyTariff - AggregationCheckpoint
Note on C23: Author: Acceptance Criteria: - Relationships mapped - Composite keys mapped - Indexes mapped
Note on C24: Author: Goal: - Database becomes deployable.
Note on C28: Author: Acceptance Criteria: - Telemetry queries benchmarked - Aggregation queries benchmarked
Note on C29: Author: Goal: - Receive and persist telemetry.
Note on C31: Author: Topics: - energy/{monitorId}/telemetry - energy/{monitorId}/heartbeat
Note on C32: Author: Acceptance Criteria: - Invalid payloads rejected - Schema version validated
Note on C33: Author: Acceptance Criteria: - Telemetry stored successfully - High-volume ingestion tested
Note on C34: Author: Acceptance Criteria: - LastHeartbeat updated
Note on C35: Author: Goal: - Generate analytical projections.
Note on C36: Author: Creates: - TelemetryMinute
Note on C37: Author: Creates: - TelemetryHourly
Note on C38: Author: Creates: - TelemetryDaily
Note on C39: Author: Acceptance Criteria: - Recover after restart - No duplicate aggregation
Note on C40: Author: Goal: - Expose business capabilities.
Note on C44: Author: Acceptance Criteria: - Only one active assignment - Previous assignment automatically closed
Note on C46: Author: Examples: - Daily - Hourly - Realtime
Note on C47: Author: Goal: - System works as a complete platform.

## Claro
TÍTULO DO PROJETO
Nome da empresa |  |  |  |  | Legenda: | No prazo |  |  |  |  | Baixo risco |  |  |  |  | Médio risco | [5 empty] | Alto risco |  |  |  |  | Não atribuído
Líder do Projeto
Data de Início do Projeto: | 2026-07-18 |  |  |  |  | julho | [13 empty] | agosto | [34 empty] | setembro
Incremento de Rolagem: | 1 | time axis 2026-07-19 to 2026-09-12
Descrição do marco | Categoria | Atribuído a | Progresso | Início | Dias | time axis 2026-07-19 to 2026-09-12
TÍTULO 1
Tarefa 1 | Objetivo | Nome | 25% | 2026-07-18 | 3 | 2026-07-19: 2; 2026-07-20: 2
Tarefa 2 | Marco |  |  | 2026-07-23 | 1 | bar: 2026-07-23
Tarefa 3 | Baixo risco |  | 50% | 2026-07-15 | 10
Tarefa 4 | Marco |  |  | 2026-08-07 | 1 | bar: 2026-08-07
Tarefa 5 | Médio risco |  | 10% | 2026-07-24 | 6
TÍTULO 2
Tarefa 1 | Alto risco |  | 60% | 2026-07-24 | 13
Tarefa 2 | No prazo |  | 50% | 2026-07-26 | 9
Tarefa 3 | Baixo risco |  | 33% | 2026-07-31 | 11
Tarefa 4 | Marco |  |  | 2026-08-02 | 1 | bar: 2026-08-02
Tarefa 5 |  |  |  | 2026-08-03 | 24
TÍTULO 3
Tarefa 1 | No prazo |  |  | 2026-08-02 | 4
Tarefa 2 | Médio risco |  |  | 2026-08-05 | 14
Tarefa 3 | No prazo |  |  | 2026-08-20 | 6
Tarefa 4 | Objetivo |  |  | 2026-08-24 | 3 | 2026-08-24: 2; 2026-08-25: 2; 2026-08-26: 2
Tarefa 5 | Baixo risco |  |  | 2026-07-24 | 19
TÍTULO 4
Tarefa 1 |  |  |  | 2026-08-27 | 15
Tarefa 2 |  |  |  | 2026-09-10 | 5
Tarefa 3 | Marco |  |  | 2026-10-22 | 1
Tarefa 4
Tarefa 5
Para adicionar mais dados, insira novas linhas ACIMA desta.

## Cor
TÍTULO DO PROJETO
Nome da empresa |  |  |  |  | Legenda: | No prazo |  |  |  |  | Baixo risco |  |  |  |  | Médio risco | [5 empty] | Alto risco |  |  |  |  | Não atribuído
Líder do Projeto
Data de Início do Projeto: | 2026-07-18 |  |  |  |  | julho | [13 empty] | agosto | [34 empty] | setembro
Incremento de Rolagem: | 1 | time axis 2026-07-19 to 2026-09-12
Descrição do marco | Categoria | Atribuído a | Progresso | Início | Dias | time axis 2026-07-19 to 2026-09-12
TÍTULO 1
Tarefa 1 | Objetivo | Nome | 25% | 2026-07-18 | 3 | 2026-07-19: 2; 2026-07-20: 2
Tarefa 2 | Marco |  |  | 2026-07-23 | 1 | bar: 2026-07-23
Tarefa 3 | Baixo risco |  | 50% | 2026-07-15 | 10
Tarefa 4 | Marco |  |  | 2026-08-07 | 1 | bar: 2026-08-07
Tarefa 5 | Médio risco |  | 10% | 2026-07-24 | 6
TÍTULO 2
Tarefa 1 | Alto risco |  | 60% | 2026-07-24 | 13
Tarefa 2 | No prazo |  | 50% | 2026-07-26 | 9
Tarefa 3 | Baixo risco |  | 33% | 2026-07-31 | 11
Tarefa 4 | Marco |  |  | 2026-08-02 | 1 | bar: 2026-08-02
Tarefa 5 |  |  |  | 2026-08-03 | 24
TÍTULO 3
Tarefa 1 | No prazo |  |  | 2026-08-02 | 4
Tarefa 2 | Médio risco |  |  | 2026-08-05 | 14
Tarefa 3 | No prazo |  |  | 2026-08-20 | 6
Tarefa 4 | Objetivo |  |  | 2026-08-24 | 3 | 2026-08-24: 2; 2026-08-25: 2; 2026-08-26: 2
Tarefa 5 | Baixo risco |  |  | 2026-07-24 | 19
TÍTULO 4
Tarefa 1 |  |  |  | 2026-08-27 | 15
Tarefa 2 |  |  |  | 2026-09-10 | 5
Tarefa 3 | Marco |  |  | 2026-10-22 | 1
Tarefa 4
Tarefa 5
Para adicionar mais dados, insira novas linhas ACIMA desta.